1624758v.2 0/0/0000

CONSULTING AGREEMENT

SERVICES

Based on discussions between the Guttmacher Institute and Fryda Guedes, as it relates to  [building legislative database], from the date of execution through [August 15th, 2025], you  agree to carry out the activities as described below. The Guttmacher Institute shall pay you  a fee of [$150/per hour].

Detail milestones/ deliverables/ applicable reporting requirements and timeline.  Policy Tracker Implementation Timeline

(Based on 20 hours/week availability)

Overview

Total Project Duration: ~32 weeks

ξ Phase 1: 8-9 weeks

ξ Phase 2: 12-13 weeks

ξ Phase 3: 12-13 weeks

Timeline

Phase 1: Replacement of Access Database (8-9 weeks)

ξ Weeks 1-3: Infrastructure & StateNet

ξ Weeks 4-6: Airtable & Data Flow

ξ Weeks 7-9: Testing & Transition

Phase 2: Enhanced Structure (12-13 weeks)

ξ Weeks 10-13: Enhanced Airtable

ξ Weeks 14-19: BigQuery Implementation

ξ Weeks 20-22: Dashboard & Training

Phase 3: Full Platform (12-13 weeks)

ξ Weeks 23-26: Advanced BigQuery

ξ Weeks 27-30: API Development

ξ Weeks 31-34: Final Implementation

Project Milestones

Phase 1 Milestones

ξ StateNet data successfully flowing to Airtable

ξ Team processing bills in new system

1624758v.2 0/0/0000

ξ Export matching current format

ξ Access system successfully backed up  ξ Team trained on basic workflows

Phase 2 Milestones

ξ Enhanced categorization implemented  ξ QA workflow optimized

ξ Basic dashboard operational

ξ Initial BigQuery transformations working  ξ Team comfortable with advanced features

Phase 3 Milestones

ξ API endpoints operational

ξ Drupal integration complete

ξ Advanced analytics dashboard live  ξ Performance metrics meeting targets  ξ Full documentation delivered

Delivery Checkpoints

Weekly:

ξ Progress update

ξ Issue review

ξ Priority adjustment

ξ Risk assessment

Monthly:

ξ Milestone review

ξ Demo session

ξ Feedback collection

ξ Planning adjustment

Labor Costs by Phase

Phase 1: Access Replacement (8-9 weeks) Infrastructure & StateNet: 30 hours

Airtable & Data Flow: 30 hours

Testing & Transition: 20-30 hours

----------------------------

Phase 1 Total Hours: 80-90 hours

Phase 1Total Cost: $12,000 - $13,500

Phase 2: Enhanced Structure (12-13 weeks) Enhanced Airtable: 40 hours

BigQuery Implementation: 60 hours  Dashboard & Training: 20-30 hours  ----------------------------

Phase 2Total Hours: 120-130 hours  Phase 2 Total Cost: $18,000 - $19,500

Phase 3: Full Platform (12-13 weeks) Advanced BigQuery: 40 hours

API Development: 40 hours

Final Implementation: 40-50 hours  ----------------------------

Phase 3Total Hours: 120-130 hours  Phase 3 Total Cost: $18,000 - $19,500  Overall Total Cost: $48,000 - $52,500